## Sheet1
Phase | Task | Priority
Foundation Setup | Set up Symfony 6 project and directory structure | High
Foundation Setup | Configure MySQL 8 database | High
Foundation Setup | Integrate SonataAdminBundle | High
Foundation Setup | Integrate SonataMediaBundle with file/image providers | High
Foundation Setup | Configure translation support and locales | High
Foundation Setup | Set up bundle registration and base config | High
Entity & Admin Development | Implement Doctrine entities with fields and relationships | High
Entity & Admin Development | Create admin class: Projects | High
Entity & Admin Development | Create admin class: Buildings | High
Entity & Admin Development | Create admin class: Real Estate Objects | High
Entity & Admin Development | Create admin class: Object Types | High
Entity & Admin Development | Create admin class: Statuses | High
Entity & Admin Development | Create admin class: Listing Types | High
Entity & Admin Development | Create admin class: Renovation Types | High
Entity & Admin Development | Create admin class: Room Definitions | High
Entity & Admin Development | Create admin class: Custom Attributes | High
Entity & Admin Development | Create admin class: Documents | High
Entity & Admin Development | Implement gallery/image logic with sorting | High
Entity & Admin Development | Add Sonata form customization for translations, file uploads | High
Entity & Admin Development | Seed test data (optional) | Medium
Public Website (Twig) | Implement object listing page | Medium
Public Website (Twig) | Apply AJAX filtering with ObjectFilterService | Medium
Public Website (Twig) | Implement pagination or infinite scroll | Medium
Public Website (Twig) | Implement object detail page with gallery, floor plan, documents | Medium
Public Website (Twig) | Build responsive layout with Tailwind or Bootstrap | Medium
API Development | Create ObjectApiController - /api/objects | Medium
API Development | Create ObjectApiController - /api/objects/{id} | Medium
API Development | Integrate token-based access control | Medium
API Development | Format consistent JSON schema | Medium
Advanced Features & Polish | Implement Favorites system (JavaScript + localStorage) | Medium
Advanced Features & Polish | Create PDF HTML template and render route | Medium
Advanced Features & Polish | Configure meta title/description and slug generation | Medium
Advanced Features & Polish | Enable translation editing in admin forms | Medium